## Client management & Engagement
Module |  | Task | Steps | Expected Result | Pass/Fail | Comments
Engage | Advisor | Create Avisor | 1. Navigate to Engage > Advisor > Advisor 2. Click on 'Add' 3. Enter advisor details 4. Save | Advisor is created successfully.
|  | Create Advisor Group | 1. Navigate to Engage > Advisor > Group 2. Click on 'Add' 3. Enter group details 4. Save | Advisor group is created successfully.
| Lead | Create Lead | 1. Navigate to Engage > Client > Lead 2. Click on 'Add' 3. Enter lead details 4. Save | Lead is created successfully.
|  | Assign Lead to an Advisor group | 1. Navigate to Engage > Client > Lead 2. Select a lead record 3. Click on 'Assign' 4. Save | Lead has been assigned successfully.
|  | Convert Lead to Client | 1. Navigate to Engage > Client > Lead 2. Select a lead record 3. Click on 'Convert' 4. Verify Lead as a Client record | Lead has been converted to a client successfully.
| Client | Create Client | 1. Navigate to Engage > Client > Client 2. Click on 'Add' 3. Enter client details 4. Save | Client is created successfully.
|  | Create Client Group | 1. Navigate to Engage > Client > Group 2. Click on 'Add' 3. Enter group details 4. Save | Client group is created successfully.
|  | Upload KYC Documents | 1. Navigate to Client > Client 3. Select a client 3. Click on 'Engage' 4. Click on 'KYC' 5. Upload KYC documents | KYC documents are uploaded and visible in the client's profile.
| Log Case |  | 1. Navigate to Engage Module 2. Click on 'Log Case' 3. Enter case details 4. Save | Case is logged successfully.
| Send Emails |  | 1. Navigate to Comminications > Email 2. Click on 'Add' 3. Compose email 4. Send | Email is sent successfully.
Report | Generate Report |  | 1. Navigate to Report Module 2. Select report type 3. Generate report | Report is generated successfully.

## Finance
Module | Task | SubTask | Steps | Expected Result | Pass/Fail | Comments
Finance | Currency | create code | 1. Navigate to Finance > Currency > Code 2. Click on 'Add' 3. Enter Code Details 4.Save
|  | create rate | 1. Navigate to Finance > Currency > Rate 2. Click on 'Add' 3. Enter Rate Details 4.Save
| Company | Create Entity | 1. Navigate to Finance > Company > Entity 2. Click on 'Add' 3. Enter Company Details 4.Save
|  | Create Account | 1. Navigate to Finance > Company > Entity 2. Click on 'Add' or 'upload' 3. Enter Account Details or upload populated file 4.Save
| Ledger | Create Period | 1. Navigate to Finance > Ledger > Period 2. Click on 'Add' 3. Enter Period Details 4.Save
|  | Create Journal | 1. Navigate to Finance > Ledger > Journal 2. Click on 'Add' to add a single journal 3. Enter Period Details 4.Save 5. Click on 'Upload' to upload the populated journal file 6. Click on 'Close Year' to close the period(year) 7. Click on ' Revalue FC Accounts' to revalue FC accounts
|  | Create Prepaid Expense | 1. Navigate to Finance > Ledger > Prepaid expenses 2. Click on 'Add' or 'upload' 3. Enter Prepaid Expenses Details or upload populated file 4.Save
|  | Create Accrued Expense | 1. Navigate to Finance > Ledger > Accrued expenses 2. Click on 'Add' or 'upload' 3. Enter Accrued Expenses Details or upload populated file 4.Save
|  | Create Asset Group | 1. Navigate to Finance > Ledger > Asset Group 2. Click on 'Add' 3. Enter Asset Group Details 4.Save
|  | Create Asset | 1. Navigate to Finance > Ledger > Fixed Assets 2. Click on 'Add' or 'upload' 3. Enter Fixed Assets Details or upload populated file 4.Save
| Statement | View Ledger, Client, Fund, Chart, GL Balance, GL Transactions, Trial Balance, Product Balance, Futures Positions, Balance Sheet, Profit & Loss and Asset & Liability Mgmt | 1. Go to Finance > Statement and select the statement. 2. Enter the required details. 3. Click View, Download, Print, or Generate to perform the desired action.
| Treasury | Create Treasury Book | 1. Navigate to Finance > Treasury > Book 2. Click on 'Add' 3. Enter Treasury Book Details 4. Configure the GL Accounts 5. Save
|  | Create Treasury Account | 1. Navigate to Finance > Treasury > Account 2. Click Add 3. Enter the treasury account details 4. Click Save
|  | Create Counterparties | 1. Navigate to Finance > Treasury > Counterparties 2. Click on 'Add' 3. Enter Counterparties Details 4. Save
|  | Create Transaction - Fixed income | 1. Navigate to Finance > Treasury > Transactions > Fixed Income 2. Click on 'Add' for a single investment or "upload" 3. Enter Fixed Income Details 4. Save 5. you can search for investments using the different filter options
|  | Create Transaction - Money Market | 1. Navigate to Finance > Treasury > Transactions > Money Market 2. Click on 'Add' for a single investment or "upload" 3. Enter Money Market Investment Details 4. Save 5. you can search for investments using the different filter options
|  | Create Transaction - Placement | 1. Navigate to Finance > Treasury > Transactions > Placement 2. Click on 'Add' for a single investment or "upload" 3. Enter the placement Details 4. Save 5. you can search for investments using the different filter options

## Operations
Module | Task | SubTask | Steps | Expected Result | Pass/Fail | Comments
Engage | Client | View Client | 1. Navigate to Engage > Client > Client 2. Click on 'View Client' 3. Select a client 2. Click on 'Engage' | Client details are displayed correctly.
|  | Edit Client | 1. Navigate to Engage > Client > Client 2. Select a client 2. Click on 'Edit' 3. Update details 4. Save | Client details are updated successfully.
| Client Group | View Client Group | 1. Navigate to Engage > Client > Group 2. Select a Client Group | Client group details are displayed correctly.
|  | Edit Client Group | 1. Navigate to Engage > Client > Group 2. Select a Client Group 3. Update details 4. Save | Client group details are updated successfully.
| View KYC |  | 1. Navigate to Client > Client 3. Select a client 3. Click on 'Engage' 4. Click on 'KYC' 5. View uploaded KYC documents | KYC documents are displayed correctly.
Invest | Manage Branch |  | 1. Navigate to Invest > Branch 2. Add/Edit branch details 3. Save | Branch is created successfully.
| Manage Investment Interest |  | 1. Navigate to Invest > Account > Interest 2. Add/Edit interest configuration 3. Save | Investment interest is created successfully.
| Manage Investment Commission |  | 1. Navigate to Invest > Account > Commission 2. Add/Edit Commission configuration 3. Save | Investment Commission is created successfully.
| Manage Investment Tax |  | 1. Navigate to Invest > Account > Taxes 2. Add/Edit tax configuration 3. Save | Investment Tax is created successfully.
| Manage Investment Fee |  | 1. Navigate to Invest > Account > Fees 2. Add/Edit Fee configuration 3. Save | Investment Fee is created successfully.
| Manage Investment Product |  | 1. Navigate to Invest > Account > Product 2. Add/Edit product configuration 3. Save NOTE: This is also where you have the global configuration of margin accounts | Investment product is created successfully.
| Investment Account | Create Investment Account | 1. Navigate to Invest > Account > Account 2. Click on 'Add' 3. Enter details 4. Save | Investment account is created successfully.
|  | Approve Investment Account | 1. Navigate to Invest > Account > Account 2. Select account 3. Click on 'Edit' 4. Click on 'Approve'
| Cash transaction | Create Cash transaction | 1. Navigate to Invest > Account > Cash 2. Click on 'Add' 3. Enter details to deposit/withdraw cash 4. Save | Cash transaction is created successfully.
|  | Update a Cash Transaction | 1. Navigate to Invest > Account > Cash 2. Select transaction 3. Click on 'Edit' 4. Edit details 5. Save | Cash transaction is updated successfully.
|  | Approve a Cash Transaction | 1. Navigate to Invest > Account > Cash 2. Select transaction 3. Click on 'Edit' 4. Click on 'Approve' | Cash transaction is approved successfully.
|  | Post a Cash Transaction | 1. Navigate to Invest > Account > Cash 2. Select transaction 3. Click on 'Edit' 4. Click on 'Post' | Cash transaction is posted successfully.
|  | Reverse a Cash Transaction | 1. Navigate to Invest > Account > Cash 2. Select transaction 3. Click on 'Edit' 4. Click on 'Reverse' | Cash transaction is reversed successfully.
| Create Account Lien |  | 1. Navigate to Invest > Account > Lien 2. Click on 'Add' 3. Enter lien details 4. Save | Cash is deposited or withdrawn from investment account successfully.
| Manage Agents | Create Agent | 1. Navigate to Invest > Trade > Agents 3. Add/Edit agent details 4. Save | Agents are managed successfully.
|  | Update an Agent | 1. Navigate to Invest > Trade > Agents 2. Select agent 3. Click on 'Edit' 4. Edit details 5. Save
|  | Attach Agent to a Client | 1. Navigate to Invest > Account > Account 2. Select account 3. Click on 'Edit' 4. Attach agent 5. Save
| Manage Brokers |  | 1. Navigate to Invest > Trade > Brokers 3. Add/Edit broker details 4. Save | Brokers are managed successfully.
| Manage Registrars |  | 1. Navigate to Invest > Trade > Registrars 3. Add/Edit registrar details 4. Save | Registrars are managed successfully.
| Manage Custodians | Create Custodian | 1. Navigate to Invest > Trade > Custodians 3. Add/Edit custodian details 4. Save | Custodians are managed successfully.
|  | Update a Custodian | 1. Navigate to Invest > Trade > Custodians 2. Select custodian 3. Click on 'Edit' 4. Edit details 5. Save
|  | Attach a Custodian to a Client | 1. Navigate to Invest > Account > Account 2. Select account 3. Click on 'Edit' 4. Attach custodian 5. Save
| Manage Holidays |  | 1. Navigate to Invest > Trade > Holidays 3. Add/Edit holiday details 4. Save | Holidays are managed successfully.
Report | Generate Reports |  | 1. Navigate to Report 2. Select report type 3. Generate report | Report is generated successfully.
System | Run End of Day |  | 1. Navigate to System > End of Day > Invest 2. Execute End of Day process | End of Day process is completed successfully.

## Trading
Test Suite | Task
Session | Logon
Logout
Change Password
Submit order outside market session
Sumit order during market session
Account | Submit order using an active account
Submit order using an inactive account
Account Number | Submit order with Valid account number
Submit order with invalid account number
Submit order with Valid account number
Account balance | Submit buy order with sufficient account balance
Submit buy order with insufficient account balance
Position balance | Submit sell order with sufficient position balance
Submit sell order with insufficient position balance
Submit buy order with sufficient account balance
Submit buy order with sufficient account balance
Order Types | Submit a Buy Market Order that is Rejected due to empty book
Submit a Sell Market Order that is Rejected due to empty book
Submit a Buy Market Order that is converted to limit order after partial fill
Submit a Sell Market Order that is converted to limit order after partial fill
Submit a Buy Market Order that is filled
Submit a Sell Market Order that is filled
Submit a Buy Limit Order that Rests in the Book
Submit a Sell Limit Order that Rests in the Book
Submit a Buy Limit Order that is rejected when price limit exceeded
Order Validity | Submit an All or None order that is killed
Submit an All or None order that is filled
Order Cancel | Submit and Cancel Order
Cancel order after partial fill
Cancel all orders
Cancel all orders for security
Order Modification | Modify price of order
Modify quantity of order
Modify price of order to trigger execution
Modify quantity of order after partial fill
Modify expiration date of order
Modify order validity
Modify order from type limit to type market
Modify AON order to create partial fill
Modify account of order
Order Execution | Submit order that receives single fill
Submit order that receives multiple partial fills
Order Status | Request status for a single order
Request status of all orders
Bonds | Submit a Buy Limit Order using yield
Submit and Cancel Bond Order
Modify yield of bond order
Submit bond order that receives single fill

## IT Team
Module | Task | Steps | Expected Result | Pass/Fail | Comments
System | Create System Users | 1. Navigate to System > Team > User 2. Click on 'Add' 3. Enter user details 4. Save | User is created successfully. User recieve Sign up email and logs in successfully | Pass | ok, but Administrators should get email notifications when a new user registers.
System | Manage User Groups and Roles | 1. Navigate to System > Team > Groups 2. Click on 'Add' 3. Create/Edit user groups 4. Assign roles 5. Save | User groups and roles are managed successfully. | Pass | Assigning roles to Groups is cumbersome. please review